## Slide 1
An orientation to the Department of Information Technology (DoIT)
Enterprise Project Management Office (EPMO) & State of New Mexico’s
Project Management (PM) processes and methodologies
for managing your way to successful information technology projects.
PM Express
EPMO Mission: Enabling successful information technology initiatives and supporting business objectives
September 2024

## Slide 2: PM Express Content
The following state project management processes are presented in this document:
Project Certification Committee
  Purpose
  Schedule
  Technology Exceptions
  Committee and Agency Participants
  Agency Responsibilities
  Gates and Phases
  Presentation
  Certification
  Monthly Reports
  IV&V
Technical Architecture Review Committee
  Cloud-based or Hosted Solutions
  Other Solutions
Information Technology Agreements

## Slide 3: Project Certification Committee (PCC): Purpose
The Project Certification Committee (PCC) evaluates project readiness and ensures that projects satisfy criteria established by the DoIT Cabinet Secretary-State Chief Information Officer (CIO).
PCC applies to certification of information technology projects undertaken by executive agencies meeting one or more of the following criteria for IT project funds to be released in a phased manner, regardless of the source of funds:
  project is required to undergo phased certifications as a result of the appropriation or grant;
  project is a subsequent or interrelated project to a previously certified project;
  project cost is equal to or in excess of $100,000.00;
  project is one deemed appropriate by the DoIT Cabinet Secretary, who is also the State CIO.
One example of a project required to undergo PCC as a result of the appropriation, is a project funded through the computer systems enhancement fund, also known as C2.
Even if a C2 project amount is less than $100,000.00, the project must be certified or a Request for Project Certification Exception and Waiver Form must be completed, emailed to Exception.Requests@doit.nm.gov and approved by the Exception Request Committee.

## Slide 4: PCC: Schedule
PCC is currently held via Teams and is scheduled on the 4th Monday of the month and begins at 9:00 am. The exceptions are the November and December meetings, which are held on the 3rd Monday of the month.
When PCC is onsite, it is held at the NM State Capitol, unless otherwise stated on the meeting invitation and agenda.
All PCC documentation must be emailed to EPMO@doit.nm.gov by the scheduled date in the month you are attending PCC.
A copy of the FY23 schedule is included on the next slide and is posted on the DoIT EPMO website in the PCC and TARC Schedule section.
To schedule, please email EPMO@doit.nm.gov at least two weeks prior to the date documents are due.
PCC Documentation is reviewed and returned to you by the following week with feedback, comments or questions for you to address.
Finalized documentation with all track changes accepted or rejected and all comments removed are due by 5pm on Friday, allowing Monday for a final review and posting to the DoIT EPMO website.

## Slide 5: PCC: FY25 Schedule

## Slide 6: PCC: Technology Exceptions
There are additional PCC requirements that must be completed and approved by DoIT if the project’s IT solution deviates from the standard State system architecture.
If the project technology is hosted or cloud-based, a completed System Hosting Evaluation Questionnaire must be emailed to exception.requests@doit.nm.gov.
The purpose of the System Hosting Evaluation Questionnaire is for the agency to present the information and diagrams related to the architecture, data and security components of the selected solution.
If the project technology deviates from the standard State system architecture and is not a hosted or cloud-based solution a completed Request for IT Exception Form must be emailed to exception.requests@doit.nm.gov.
The Request for IT Exception Form is different from the Request for Project Certification Exception and Waiver Form.
The purpose of the Request for IT Exception Form is for the agency to present the selected architecture to DoIT for review the Request for Project Certification Exception and Waiver Form is used to request an exception to a certified project’s PCC, TARC or IV&V requirements.

## Slide 7: PCC: Committee and Agency Participants
The DoIT Cabinet Secretary-State CIO serves as the PCC chair.
PCC members consist of the DoIT Deputy CIO, DoIT General Counsel, DoIT Chief Information Security Officer, DoIT Application Development Manager, DoIT EPMO Director, DoIT Special Projects Manager and IT and finance representatives from the Public Regulations Commission, Taxation and Revenue Department, State Purchasing Division, Department of Finance and Administration and the Legislative Finance Committee.
Agencies must be represented by the executive sponsor; project leads and a business representative.
Prior to scheduling for PCC, the agency must ensure adequate planning appropriate to the certification gate requested and ensure that the required documentation is completed.

## Slide 8: PCC: Agency Responsibilities
    The agency must appoint a qualified lead project manager (PM).
    If the agency hires a contract PM, the CIO or lead project manager is responsible for ensuring that the contracted PM is managed in the best interests of the state and is knowledgeable in completing the DoIT PCC and TARC documentation.
    Upon DoIT request, the PM must provide access to all project management deliverables such as project plans, project schedules, initial and periodic risk assessments, quality plans and strategies, periodic project reports, requirements and design documents.
    The PM must prepare and submit the monthly status report by the 10th of each month.
    The PM must include independent verification and validation (IV&V) as part of the project or request a waiver using the Request for Project Certification Exception-PCC-IV&V-TARC Waiver form on the DoIT EPMO website in the Oversight and Exception Process section.

## Slide 9: PCC: Agency Responsibilities
    Review the PCC schedule ahead of time to plan project certification attendance to ensure that phase and funding approval is conducted in time to not disrupt the project.
    Do not plan on attending PCC and TARC in the same month.
Certification Request Forms for each of the project phases including Initiation, Planning, Implementation, Closeout and Change, can be found on the DoIT EPMO website in the Certification Request Forms section.
Charter and Project Management Plan templates are available on the DoIT EPMO website in the Project Certification Templates section.
The Gates and Phases section that follows, illustrates each phase and the documentation required to certify for each phase.

## Slide 10: PCC Gates and Phases

## Slide 11: PCC Gates and Phases: Initiation
Initiation Certification and Phase funding is requested by an agency for use in initial project setup activities such as defining governance, stakeholders, project objectives, high level scope, approach/phases, project charter, conducting research and analysis, procurement planning, developing Independent Verification and Validation (IV&V) plan and contract; developing initial project management plan with rough order magnitude estimates, etc.
Note: Waiver of the IV&V requirement requires specific written approval by the DoIT Cabinet Secretary.
Required Documentation: The Initiation Request for Certification and Release of Funds form, Project Charter and a presentation.

## Slide 12: PCC Gates and Phases: Planning
Planning Certification and Phase is requested by an agency to request funds needed to complete all planning needed to successfully accomplish project objectives.
This request is for activities such as procuring project manager or business analyst services to assist with planning, defining & baselining, scope, schedule, budget, quality metrics, requirements, business processes, plans for procurement, communication, change management, risk/issue management, project management (PMP), technical planning, system design, security planning, business continuity/disaster recovery planning, etc.
IV&V consultant should be engaged early on during the Planning Phase.
Required Documentation: The Project Planning Request for Certification and Release of Funds, Project Charter (if an update is needed), PMP and a presentation.

## Slide 13: PCC Gates and Phases: Implementation
Implementation Certification and Phase is for project execution. Prior to certifying for Implementation, once the technical solution has been selected, the project must be approved or waived by the TARC.
This request is for funds needed to execute, track and manage actual work of the project/phase in accordance with plans. Typical activities could include joint application design sessions, procurements (RFPs, contracts, etc.), contract and vendor management, build, buy, modify, configure, implement, testing, training, rollouts, transition to operations, etc.
The project should have a qualified PM structure to manage, track, monitor and report on progress.
IV&V consultant should be actively engaged in the project with IV&V reports delivered to the agency and EPMO@doit.nm.gov.
Required Documentation: The Implementation Certification Request, updated/final PMP, a presentation and the most recent IV&V report.

## Slide 14: PCC Gates and Phases: Closeout, Change or Update
Closeout Certification and Phase is the termination or completion of the project. Prior to Closeout, all procurements must be closed.
Required Documentation: The Project Closeout Certification Request and a presentation. Closeout Certification must include lessons learned and any benefits realized.
Change Request may be requested anytime during the project and may include changes to baselined scope, schedule, budget, project phase, technical solution or other critical changes in the project, including when additional funds become available, etc.
Required Documentation: The Change Request for Certification and Release of Funds, a presentation and an updated PMP. A results update should be included in the certification request description that includes lessons learned and performance improvements realized in the completed phases.
An Update is normally requested by the PCC but may be provided by the agency at any time during the project to report on progress.
Required Documentation: A presentation.

## Slide 15: PCC: Presentation
Include the following items in your presentation:
  Cover slide including the project name, phase being requested, names and roles of the team presenting and the PCC date
  Agency mission, project stakeholders and governance (for Initiation phase)
  An overview that includes business need, project objectives, planned technical and procurement approach (All phases)
  Work performed to date and the work to be performed in the phase being certified (All phases)
  Appropriation history, certification history, project and product deliverables with timeline, estimated project budget, and procurement information (All phases)
  Include latest IV&V summary and identify technical and security approach, risks, issues and mitigation strategies (Planning, Implementation)
  Performance metrics improvements and/or benefits realized, IV&V summary, scope verification, schedule and cost comparison, transition to operations, lessons learned (Closeout)
Include a subject matter expert who can speak in detail regarding the technical and business aspects of the project and a representative from the business side who is very familiar with the project and how the end users will utilize it.

## Slide 16: PCC: Presentation
For onsite meetings, arrive 15 minutes prior to your assigned time and take a seat in the audience area.
Bring 12 printed copies of the presentation and certification request to the hearing to be delivered to EPMO staff, who will hand them out to the committee.
Plan to present for no more than 20 minutes, allowing 10 minutes at the end of your presentation for PCC questions.
Please wear business attire and when called to present, take a seat at the hearing table.
Begin your presentation by addressing the chair first, then members of the committee. “Mr. Chairman and members of the committee…” then continue by introducing yourself and the presenters.
The same protocol is used when responding to questions from the committee. “Mr. Chairman and members of the committee…” then the response.
After you complete your presentation and respond to questions, the chair will make a motion to vote and the PCC will pass or deny the project with two votes.
For DoIT Project Certifications, the DoIT Cabinet Secretary-State CIO recuses himself from the certification vote and a non-DoIT designee serves as Chair.

## Slide 17: PCC: Certification
Upon PCC Approval and Certification, DoIT will issue a letter to DFA, your cabinet secretary and CIO authorizing the release of funds with either:
Release of Funds - No requirements or contingencies.
Release of Funds with Requirements - Agency will receive the released funds, however, Agency must complete the requirements or the project will be halted.
Release of Funds Contingent Upon Completed Tasks - Agency must first complete the required contingencies prior to the release of funds.
For projects with a contingency, the project is included in the original letter and a subsequent letter will be sent once the contingency has been met.
The certification letters for each month are posted on the DoIT EPMO website in the Project Certification Committee section.

## Slide 18: PCC: Monthly Reports
For all certified projects, a monthly project report is due to EPMO@doit.nm.gov on the 10th of each month after project Initiation through project Closeout. For example, if you certify a project at the April PCC, a report will be due May 10. If you certify a project for Closeout, the final report is due on the 10th of the month following your presentation.
The Project Monthly Report Template is on the DoIT EPMO website in the Project Monthly Report section.
  Sheet One is the overall monthly status of project and key performance indicators
  Sheet Two is a detailed breakdown of milestones and progress
The data to be reported is from the previous month. For example, the June 10 report contains project activities from May.
The EPMO team reviews the reports along with IV&V reports and other project artifacts to assess project health and to provide assistance & guidance, as necessary to ensure successful outcomes.
Data from these reports are posted on a quarterly basis to the DoIT EPMO website in the EPMO Project Portfolio section. Projects with the highest dollar value or high risk/visibility are displayed in the Top Ten.

## Slide 19: PCC: IV&V
The DoIT requires all certified projects engage an IV&V contractor unless waived.
IV&V means the process of evaluating a project to determine compliance with specified requirements and the process of determining whether the products of a given development phase fulfill the requirements established during the previous stage, both of which are performed by an organization independent of the lead agency.
If you are considering an IV&V waiver, please complete a Request for Project Certification Exception or Waiver form, which can be found on the DoIT EPMO website and email it to Exception.Requests@doit.nm.gov.
The form must include a strong justification for IV&V not being needed and a description of any verification and/or validation that will occur.
Since IV&V services are expected to be active early in planning, please make your request prior to certifying for the Planning Phase.

## Slide 20: PCC: IV&V
To be considered for an IV&V waiver approval, a project must be proven to be low risk because of the scope, technology type or the agency’s or vendor’s expert knowledge of the technology. Possible reasons for waiver approval may include:
  Projects under the $100,000 certification threshold
  Projects whose only objective is to conduct research, analysis or discovery
  Projects that are operational in nature, such as a large implementation of end user hardware components
  Projects that are related to existing SHARE functionality
  Projects for which the agency has a demonstrated mastery of a technology platform or application
  Projects with agency staff experienced in project management, business analysis, software development/integration and business operations with documented project management procedures and controls
  Projects based on mature proven technology, previously successful implementations that are similar in scope with well-defined and documented repeatable processes, managed by onsite expertise that have extensive expertise related to the project

## Slide 21: PCC: IV&V
IV&V Guidance & Template is available on the DoIT EPMO website in the IV&V Template section.
Quality Assurance IV&V Guidelines
Memo on IV&V Reporting Template
When vendors have completed their reports, instruct them to email them to your agency contact and to include EPMO@doit.nm.gov.

## Slide 22: Technical Architecture Review Committee: Purpose & Requirements
Technical Architecture Review Committee (TARC) is required for all certified projects and as of December 2021, is required for any cloud-based or hosted solution.
TARC ensures adequate planning on technical aspects of a project is completed and documented and verifies compliance with the State Information Architecture.
When an agency identifies their technical solution, they should contact the Department of Information Technology (DoIT) Enterprise Project Management Office (EPMO) at EPMO@doit.nm.gov to discuss the TARC process, options and scheduling.
Depending on your technology type, possible first steps may include:
  Completing a Request for Project Certification Exception and Waiver form to request a TARC waiver.
  Completing a System Hosting Evaluation Questionnaire and emailing it to Exception.Requests@doit.nm.gov for a cloud-based or hosted solution.
  Completing an IT Exception Request Form and emailing it to Exception.Requests@doit.nm.gov for non-cloud hosted exceptions.
TARC must be approved by DoIT prior to the Implementation Phase.

## Slide 23: Technical Architecture Review Committee
Ideally, an agency should begin planning for TARC at least a month prior to documentation being delivered to EPMO.
Currently, the TARC meeting is virtual and you will receive a Teams meeting invitation, once your readiness to present is confirmed by EPMO.
When scheduled onsite, which will be indicated in an Outlook meeting invitation, the meeting is located at the DoIT First Floor Conference Room at the Simms Building.
If you intend to request a TARC waiver, your Request for Project Certification Exception and Waiver form is due no later than a month prior to TARC and is emailed to Exception.Requests@doit.nm.gov.
The lead time is to provide you sufficient time to prepare for TARC in case your request is denied.
If your TARC waiver is rejected, be prepared to continue with the standard TARC process.
If your TARC waiver is approved, your Request for Project Certification Exception and Waiver form will be returned with DoIT signature and date.

## Slide 24: Technical Architecture Review Committee
TARC is chaired by the DoIT Deputy Chief Information Officer (CIO) and committee members include DoIT technical subject matter experts in security and networks.
Agencies presenting at TARC should be represented by the CIO or IT Lead and other technical experts on the project.
If the TARC denies continuation, they will provide requirements needed to successfully meet TARC requirements.
If the TARC approves continuation, a memo is emailed to the agency CIO or IT Lead indicating approval and a recommendation to continue implementation discussions with DoIT Enterprise Services to ensure a successful Implementation.
TARC is currently scheduled on the fourth Monday of each month with the exception of November and December that have month end holidays, in which case, TARC is conducted on third Monday of the month.
Once TARC is approved, an agency may proceed to PCC to conduct their Implementation Phase requirements.

## Slide 25: Technical Architecture Review Committee
The following calendar screenshot includes dates when the initial documentation is due, when you can expect the DoIT reviewed documents to be returned to you, when finalized documentation is due and the date of the TARC meeting. Check the full schedule, which is posted on the DoIT EPMO website in the FY2025 PCC and TARC Schedule section to plan your TARC and PCC attendance.
*Draft documents must be received by 9 am. **Final documents must be received by 5 pm.

## Slide 26: TARC: Cloud-Based and Hosted Solutions
As of March 2023, documentation required for TARC changed.
For a cloud-based or hosted solution, only one document is required to initiate TARC, a completed System Hosting Evaluation Questionnaire.
To eliminate redundant questions and multiple documents, the new System Hosting Evaluation Questionnaire combines information formerly requested in the:
System Hosting Evaluation Questionnaire,
IT Exception Request Form,
Security Questionnaire, and
System Design Document Template.
The new System Hosting Evaluation Questionnaire must be thoroughly completed by the agency, with all questions addressed, and any follow-up questions from the TARC answered.
If the System Hosting Evaluation Questionnaire is thoroughly completed and approved by DoIT, a presentation is not required.

## Slide 27: TARC: Cloud-Based and Hosted Solutions
Documents requested in the new questionnaire are:
  A system architecture document that includes a summary of the software architecture and different tiers/layers. For example, database, application, business and presentation that are included in the solution.
  An independent security assessment report of the solution and application, if applicable. If an assessment has not been conducted, you will be asked to provide an estimated date for when it will be done.
Once your documentation is reviewed and approved by the TARC, your form will be signed by DoIT indicating approval to proceed with the Implementation Phase. No presentation is required.
Approval of cloud-based and hosted solutions is time bound, 1-year from the date of the approval and cannot be automatically extended.

## Slide 28: TARC: Cloud-Based and Hosted Solutions
If after TARC approval, there are no changes to the approved technology, renewal is conducted by sending your request to continue use of the solution to exception.requests@doit.nm.gov and copying your DoIT assigned EPMO project manager. You will receive an email in response once your request is approved.
If after TARC approval, there are changes to the approved technology, please email a completed System Hosting evaluation Questionnaire to exception.requests@doit.nm.gov for review.
For cloud-based and hosted solutions that are not part of the DoIT tenant, when you’re developing your information technology procurement, consider what would be required to move the solution to the DoIT cloud broker to be part of NM cloud tenant(s), to meet the objective of economies of scale.

## Slide 29: TARC: Non-Cloud Based and Non-Hosted Solutions
For any certified project that is not a cloud-based or hosted solution, the documentation has changed from the originally requested documents to one Power Point presentation.
  The presentation template includes topics and illustrations requested from each of the TARC documents previously required, such as.
  A summarized project overview & scope and details on what will be purchased as part of the solution
  A diagram of the software architecture and hardware architecture
  Information on data including type, data exchanges, applicable laws, ownership
  Security requirements such as intrusion detection, firewalls, encryption
  Monitoring and review of security logs/alerts
  End user and operational support
  Information on business continuity/disaster recovery
  Contractor agreements
  The TARC meeting is scheduled for one hour.
  The presentation, should not exceed 30 minutes, allowing 30 minutes for discussion and questions from the TARC.
  Once TARC is approved, an agency may proceed to PCC to complete the Implementation Phase requirements.

## Slide 30: Technical Architecture Review Committee
If you are presenting due to a cloud hosted exception request, the following requirements must be met, and related documentation presented to TARC:
A completed System Hosting Evaluation Questionnaire
An information technology security plan that includes an incident response plan
Proof that security controls are tested by an independent 3rd party for network, platform and cloud applications prior to production
A documented and signed cloud exit strategy that is supported by a contract exit clause
Information technology procurements must include clause to move to DoIT cloud broker to be part of NM cloud tenant(s), to meet the objective of economies of scale
Continuity plan
These requirements are time bound, 1 year from the date of the approved exception request and cannot be automatically extended.

## Slide 31: IT Professional Services Procurements
    The following IT Professional Services procurements that are deemed as professional services by the Contracts Review Bureau (CRB) must be emailed to EPMO@doit.nm.gov for review. Links to the templates are included:
      All IT Professional Services contracts in the amount of $60,000 or greater
      IT Professional Services contracts less than $60,000 that are related to a certified project, IT security, hosting or the State’s SHARE system; IT Professional Services greater than five thousand dollars ($5,000) must use the small IT Professional Services Template
      IT Professional Services Amendments
      Sole Source Determination Forms
      Request for Proposals
    If a procurement is deemed as general services and includes a hosted solution, CRB will ask that you email it to EPMO@doit.nm.gov for review.
    If a hosted solution is being purchased by a contracted vendor, the solution must follow the System Hosting Evaluation process.

## Slide 32: IT Professional Services Procurements
The EPMO will provide edits and comments in the Word version of the agreement to be addressed by the agency prior to processing for signature.
EPMO’s House Bill 2 performance measures for review of contracts is < $1 million within 5 days and > $1 million within 7 days.
EPMO may request additional reviews if the agreement requires substantial changes.

## Slide 33
Small IT Professional Services Contract Template
Only if related to
a certified project, IT security or SHARE
Always Required
Large IT Professional Services Contract Template
Vendor
Agreement
DoIT Review & Approval
Procurement
Method
Yes
$5,000 - $60,000
Yes
>=$60,000
Any Agency Approved Method
No
IT Professional Services Procurements
If deemed as IT Professional Services by CRB
Statewide Price Agreement
Sole Source Agreement
Government Purchasing Association (GSA)
Western States Contracting Alliance (WSCA)-National Association of State Procurement Officials (NASPO)
RFP/Agency Price Agreement

## Slide 34: IT Procurements
Agency level CIOs may approve IT procurements other than IT professional services agreements, such as IT purchases and/or leases for software/hardware at or below one hundred thousand dollars ($100,000) that:
  Are not restricted by IT consolidation directives; See Exceptions on the next page;
  Are included in and are consistent with the Agency IT plan, State Architectural standards and the State IT Strategic Plan;
  Are not part of an IT project or initiative requiring DoIT approval; and
  Are not deemed by the DoIT to possess substantial risk.
All IT purchases and/or leases for software/hardware which exceed one hundred thousand dollars ($100,000) are routed by DFA for DoIT approval;
All IT purchases that include hosting or system integrators that may procure hosting services on behalf of the agency;
Agreements that contain items listed on the IT Exception list such as any server or storage solutions purchase, any individual hardware or software purchase > $100K, any deviation from the state’s central communication system, require that a completed and signed IT Exception Request Form be emailed to exception.requests@doit.nm.gov.

## Slide 35: Exceptions - Executive Order (EO) 2008-11 IT Consolidation
EO 2008-11 includes “Whereas, the unnecessary duplication of technology services must be reduced and eliminated and IT investments must be managed effectively and efficiently; and the cost of government operations can be reduced through effective development, implementation and management of IT architecture, programs and services, IT operational costs can be reduced through enterprise models, and the efficient delivery of high quality government services will benefit clients and support economic development.”
The DoIT Cabinet Secretary has delegated the authority for many IT procurements and actions to the approval level of each agency CIO. However, the DoIT requires the following are reviewed and approved via the State’s EO 2008-11 exception process.
Equipment | Any server or storage solutions purchase (regardless of cost). Any individual hardware or software purchase > $100K.
Personnel | Personnel actions on existing infrastructure position requires DoIT’s approval.
Tel/Com Network ISP | Any deviation from the state’s central communication system. This includes, but is not limited to, equipment and service for telephone, networks and radio.
Hosting and Storage | All production systems should be hosted in the State’s Data Center. Any system not hosted in the data center requires DoIT approval. This includes but is not limited to websites, cloud services, SaaS, IaaS, and PaaS.
Rule | Any rule deviation must be approved by DoIT.

## Slide 36: IT Professional Services Procurements
Agencies are responsible for managing their IT agreements to ensure timely processing, award and/or renewal.
Sufficient time must be allocated for each step of the approval processes to ensure it reaches the DoIT with sufficient time for review prior to the proposed date of execution of the contract and/or agreement.
Agreements sent to DoIT for signature must be signed by the vendor, agency secretary or executive director, the agency general counsel, and Taxation and Revenue Department.
We encourage the use of DocuSign for the routing of your agreements. If you need information on the process, please contact epmo@doit.nm.gov.
If you are not currently using DocuSign, email your signed agreement to epmo@doit.nm.gov and it will be processed for DoIT signature.
Once signed, you will receive a copy via email.

## Slide 37
Agency IT Professional Service Contract, Amendment & RFP Review & Approval Process
IT Contract, Amendment and RFP eReview
IT Contract, Amendment and RFP Final Review and Signature
EPMO@doit.nm.gov is the common mailbox for all correspondence with the EPMO. Your agency’s assigned EPMO project manager can be copied, but should not be the primary contact. This mailbox is monitored regularly and will ensure the timely turn around of the eReview. Agreements considered ready for signature must be signed by the vendor, agency secretary or executive director, the agency general counsel and Taxation and Revenue Department prior to delivery to DoIT.
DoIT EPMO conducts final review and approves or processes for signature.
DoIT CIO signs contract, contract amendment or RFP cover letter.
DoIT emails agency with signed copy or approval is indicated by DocuSign.
Process via DocuSign or email to EPMO@doit.nm.gov for final review and signature by DoIT.
Agency develops contract, amendment, sole source form or RFP using standard template. It should be reviewed by the Agency’s legal, CIO & finance prior to emailing to EPMO.
Agency submits finalized Word version to EPMO@doit.nm.gov for eReview and includes a deviation memo from the agency’s legal if any changes are made to the terms and conditions.
DoIT reviews contract, amendment, sole source form or RFP and returns with comments/edits to the agency.
Agency addresses comments/edits, returns for additional review if requested or proceeds with agency signature.

## Slide 38: Useful Links
DoIT EPMO website: Compliance and Project Management - New Mexico Department of Information Technology (nm.gov)
PCC webpage: Project Certification Committee - New Mexico Department of Information Technology (nm.gov)
Templates for PCC: Compliance and Project Management - New Mexico Department of Information Technology (nm.gov)
Templates for other project documents: Project Management Templates & Guidance - New Mexico Department of Information Technology (nm.gov)
Contract Templates: Contract & RFP Templates & Guidance - New Mexico Department of Information Technology (nm.gov)
Enterprise Portfolio Reports & Presentations: Project Portfolio - New Mexico Department of Information Technology (nm.gov)
For any questions, please contact your assigned EPMO project manager or epmo@doit.nm.gov